## Package Table and Charts
Objective Code | Objective Description | Prerequisite Objectives | Prereqs Met? | Estimated TTC (low, hrs) | Estimated TTC (high, hrs) | Completed?
1.0.0 | Sand -> Si Wafer Process Estabilished |  | YES
1.1.0 | Purifying Sand into SiO2 |  | YES | 50 | 200
1.2.0 | Purifying SiO2 into 9N SiO2 | 1.1.0 | NO | 100 | 500
1.3.0 | SiO2 into Polycrystalline Si | 1.2.0 | NO | 100 | 200
1.4.0 | Polycrystalline Si into Doped Monocrystalline Si | 1.3.0 | NO | 200 | 600
1.5.0 | Boule Slicing, Wafer Polishing | 1.4.0 | NO | 30 | 200
2.0.0 | Photolithography and Chip Fabrication Process |  | YES
2.1.0 | Dummy masks for simple devices |  | YES | 1 | 8
2.2.0 | Photoresist application and development equipment |  | YES | 3 | 20
2.3.0 | Confirmed pattern transfer via masks/patterns | 2.2.0, 2.1.0, 7.3.0 | NO | 10 | 100
2.4.0 | Metal Thin Film Deposition Process confirmed | 1.5.0 | NO | 30 | 200
2.5.0 | Dry Etching process estabilished | 2.3.0 | NO | 20 | 150
2.6.0 | Oxide Growth System estabilished | 1.5.0 | NO | 20 | 80
2.7.0 | Selective Doping process estabilished | 1.5.0, 2.1.0 | NO | 40 | 200
2.8.0 | Dielectric of choice deposited onto wafer | 1.5.0 | NO | 20 | 300
3.0.0 | Die Packaging Process Complete |  | YES | 200 | 2000
4.0.0 | Characterization Equipment Acquired | 1.5.0 | NO | 0 | 0
5.0.0 | CPU Architecture Estabilished |  | YES
5.1.0 | Bus Width Selected |  | YES | 0 | 0 | YES
5.2.0 | Assembly Instruction Architecture | 5.1.0 | YES | 1 | 3 | YES
5.3.0 | ALU requirements outlined |  | YES | 1 | 3 | YES
5.4.0 | Bus Logic requirements outlined |  | YES | 1 | 2 | YES
5.5.0 | Port Requirements outlined |  | YES | 1 | 2
5.6.0 | Register File requirements outlined |  | YES | 1 | 2 | YES
5.7.0 | Control Signals Listed |  | YES | 1 | 2
6.0.0 | Logisim Simulation Completed | 5.0.0 | NO
6.1.0 | Arithmetic Logic Unit | 5.0.0, 5.3.0 | NO | 2 | 3
6.2.0 | Register File | 5.0.0, 5.6.0 | NO | 1 | 2
6.3.0 | Bus Logic | 5.0.0, 5.4.0 | NO | 3 | 5
6.4.0 | Port Handlers | 5.0.0, 5.5.0 | NO | 2 | 3
6.5.0 | EEPROM written | 5.0.0, 5.7.0 | NO | 2 | 3
6.6.0 | Full Scale Test | 6.5.0, 6.4.0, 6.3.0, 6.2.0, 6.1.0 | NO | 10 | 20
7.0.0 | CMOS TTL Schematic | 6.0.0 | NO
7.1.0 | CMOS Transistor Circuit Schematic | 6.0.0 | NO | 3 | 5
7.2.0 | CMOS Transistor Count and Critical Path Analysis | 7.1.0 | NO | 2 | 5
7.3.0 | Photolithography Mask / Pattern Designs | 2.1.0, 7.1.0 | NO | 10 | 30
8.0.0 | TBASM Assembler | 5.2.0 | YES
8.1.0 | Basic C-based file IO system |  | YES | 3 | 5
8.2.0 | Single-Pass Lexer implemented | 8.1.0 | NO | 2 | 5
8.3.0 | Macro Support incorporated into Lexer | 8.2.0 | NO | 1 | 5
8.4.0 | Instruction to Binary Output Assembler | 8.2.0 | NO | 1 | 2
8.5.0 | Functional Compiler | 8.4.0 |  | 2 | 5
8.6.0 | Self-Assembly | 8.5.0 | NO | 5 | 20
8.7.0 | Standard Macro Library | 8.3.0, 8.5.0 | NO | 10 | 20
9.0.0 | pandora Language Compiler | 8.0.0 | NO
9.1.0 | Define Language Architecture | 8.0.0 | NO | 2 | 10
9.2.0 | Single-Pass Tokenizer implemented | 8.0.0, 8.1.0 | NO | 1 | 3
9.3.0 | Implement AST generator | 9.2.0 | NO | 30 | 100
9.4.0 | Functional Compiler | 9.3.0 | NO | 20 | 100
9.5.0 | Self-Compilation | 9.4.0 | NO | 10 | 30
9.6.0 | Standard Function Library | 9.4.0 | NO | 5 | 20
10.0.0 | CPU Built on Physical Hardware | 1.0.0, 2.0.0, 3.0.0, 4.0.0, 7.0.0 | NO

## Charts Backend
Misc Charts, non Row Dependent
Objectives Remaining | 47
Objectives Finished | 5
Objective-hours Finished | 4 | 10
Objective-hours Remaining | 953 | 5163
| est. best case | est. worst case
Objective-hours Finished | 10
Objective-hours Remaining | 5163